## Risk Assessment Form
Event/Activity Risk Assessment
Identify Event or Activity:
Identify Possible Risk [What could go wrong?] | Identify Possible Triggers | Plan a Contingency Action | Responsible Person to Implement Contingency Activity

## Risk Assessment Form Example
Event/Activity Risk Assessment
Identify Event or Activity: | Table Lodge
Identify Possible Risk [What could go wrong?] | Identify Possible Triggers | Plan a Contingency Action | Responsible Person to Implement Contingency Activity
Conflict with other events. |  | Check appendant body's calendar | Herman Schwartz -complete no conflicts
Not enough food. | 70 tickets are sold. | Ticket sales cutoff 7 days before event. Add five extra dinners. | Senior Warden
Not enough meat. | Meat supplier shorted on servings. | Check count before leaving butcher. | Kitchen chairman
Kitchen ovens and refrigerators working. |  | Check 2 days before event. | Kitchen Chairman